BPSC AI Platform

Document 12 — Final Product Roadmap & Phased Implementation Plan

Purpose: Convert Documents 01–11 into one practical execution roadmap for building, refactoring, launching, and scaling the BPSC AI personal mentor platform.

Audience: Product owner, engineering team, AI/RAG engineers, DevOps, QA, content experts, business team, and Claude Code.

Status: Final implementation blueprint

# 1. Executive Summary

The BPSC AI platform should be built as an AI personal mentor, not simply an answer-checking bot. The core learning loop is QUESTION → HANDWRITTEN ANSWER → OCR/VISION → RAG EVIDENCE → EXAMINER → FEEDBACK → LEARNING PROFILE → NEXT QUESTION.

The recommended strategy is incremental. Keep the existing Node.js/Telegram product working while introducing modular boundaries around AI, RAG, evaluation, storage, jobs, analytics, and domain logic. Do not attempt a large rewrite before the critical student journey is covered by tests and observability.

Phase 0: Baseline, audit, safety, and test foundation.

Phase 1: Production-grade MVP core.

Phase 2: AI evaluation and personalized mentor.

Phase 3: Beta, analytics, monetization, and quality optimization.

Phase 4: Web/Android expansion and scale.

Phase 5: Advanced learning intelligence and defensible data moat.

# 2. Final Product Vision

Build the most useful AI-assisted BPSC answer-writing mentor for Hindi-medium aspirants by combining exam-pattern knowledge, NCERT-grounded evidence, Bihar-specific context, current affairs, handwritten-answer understanding, examiner-style evaluation, and longitudinal personalization.

Student gets the right question, not a random question.

Student can write naturally by hand.

AI evaluates against an explicit blueprint and rubric.

Feedback explains what to improve and how.

Repeated attempts create a learning profile.

Future questions adapt to demonstrated strengths and weaknesses.

Every important AI result is traceable to prompt/model/source versions.

# 3. Product North Star

| Dimension | North-Star Outcome |
| --- | --- |
| Learning | Students improve answer-writing quality over repeated attempts |
| Engagement | Students return for meaningful practice, not notifications alone |
| AI quality | Evaluation approaches qualified human examiner judgment |
| Trust | Feedback is evidence-grounded and transparent |
| Economics | AI cost per successful learning attempt remains sustainable |
| Reliability | Critical learning journey completes consistently |

# 4. Architecture Target State

Target architecture remains a modular monolith initially, with separate processes for API, workers, scheduler, and admin/web where useful. High-load components can later be extracted into services.

Node.js + TypeScript application layer.

PostgreSQL as system of record.

pgvector for initial vector retrieval.

Redis + BullMQ for asynchronous work.

S3-compatible object storage for handwritten images.

AI Gateway as the only external model-provider boundary.

RAG service/module for evidence retrieval and provenance.

Telegram as first client; Web and Android as later clients.

Centralized logs, metrics, traces, AI usage, and quality telemetry.

# 5. Phase 0 — Audit, Baseline & Foundation

| Workstream | Deliverables | Exit Criteria |
| --- | --- | --- |
| Code audit | Current modules, dependencies, risks, technical debt map | Repository documented |
| Architecture | Target module boundaries | No critical ambiguity |
| Database | Schema review and migration plan | Safe migration path |
| AI | Provider/model call inventory | All AI calls identified |
| Testing | Test runner, fixtures, baseline suite | CI can execute |
| Security | Secrets, uploads, auth review | Critical findings addressed |
| Observability | Correlation IDs, logs, AI call logs | Critical journey traceable |
| Cost | Token/call baseline | Cost per attempt measurable |

Recommended duration: approximately 1–2 weeks depending on the current codebase condition.

# 6. Phase 1 — Production-Grade MVP

## 6.1 Student Journey

Start Telegram session.

Choose subject/topic or practice mode.

Generate question from curated PYQ-informed knowledge.

Run Question Quality Checker.

Create and store Evaluation Blueprint.

Deliver question.

Accept one or multiple handwritten pages.

Store original images.

Run OCR/Vision asynchronously.

Retrieve relevant NCERT/PYQ/authoritative evidence.

Run Examiner AI.

Persist criterion scores, evidence, feedback, and confidence.

Notify student.

Update learning profile.

## 6.2 Phase 1 Scope

Telegram-first UX.

Long-answer and short-answer support.

Core BPSC subjects.

Curated PYQ dataset.

NCERT knowledge base.

Evaluation Blueprint.

Handwritten OCR pipeline.

Examiner scoring and feedback.

Basic progress history.

Admin quality-review capability.

Basic subscription/entitlement foundation if monetization is launched.

# 7. Phase 1 — Explicit Non-Goals

Do not build a full social network.

Do not build dozens of microservices.

Do not build a complex Android app before the core loop is validated.

Do not ingest the entire internet.

Do not generate expensive full model answers for every attempt.

Do not make AI scoring an official-exam claim.

Do not optimize advanced personalization before collecting reliable learning signals.

# 8. Phase 2 — AI Mentor & Personalization

Once the core loop is reliable, the platform should evolve from answer checker to mentor.

Student Skill Profile by subject/topic/criterion.

Weakness signals from repeated evaluations.

Difficulty-adjusted performance.

Adaptive question selection.

Spaced revision recommendations.

Targeted feedback on recurring errors.

Mentor conversations grounded in the student's history.

Improved question diversity and novelty.

On-demand model answers and improved-answer outlines.

Personal study plans.

# 9. Phase 2 Adaptive Learning Loop

ATTEMPT → EVALUATION → CRITERION SCORES → ERROR TAGS → SKILL PROFILE → DIFFICULTY ESTIMATE → QUESTION SELECTION → NEXT ATTEMPT

| Signal | Example Use |
| --- | --- |
| Low structure score | Recommend structure-focused questions |
| Weak factual accuracy | Recommend evidence-heavy practice |
| Repeated topic weakness | Increase topic exposure |
| Strong topic performance | Increase difficulty or reduce frequency |
| Poor conclusion/way-forward | Target questions requiring balanced conclusions |
| Improving trend | Progress difficulty gradually |

# 10. Phase 3 — Beta & Product-Market Validation

The beta phase should focus on whether the platform produces measurable learning improvement and whether students will repeatedly use and pay for it.

Invite a controlled group of BPSC aspirants.

Capture baseline answer-writing performance.

Measure repeated-attempt improvement.

Collect human-review comparisons.

Identify confusing Telegram UX steps.

Test pricing and entitlements.

Measure AI cost per active learner.

Create support and incident workflows.

Establish content review cadence.

# 11. Beta Experiment Design

| Experiment | Primary Question |
| --- | --- |
| AI feedback vs generic feedback | Does personalized feedback improve repeat attempts? |
| Adaptive vs random questions | Does adaptation improve learning? |
| Blueprint vs no blueprint | Does rubric grounding improve scoring agreement? |
| NCERT-first RAG vs broad web | Does authority improve trust and accuracy? |
| Targeted outline vs full model answer | Which gives better learning per rupee? |
| Reminder timing | Which schedule improves productive practice? |

# 12. Phase 3 Monetization

Monetization should follow demonstrated value rather than simply charging for AI tokens.

| Tier | Possible Positioning |
| --- | --- |
| Free | Limited practice and evaluation credits |
| Pro | Higher attempt limits, personalized mentor, detailed analytics |
| Premium | Advanced adaptive plans, deeper reports, model answers, priority processing |
| Institute | Admin dashboard, cohorts, assignments, analytics, future multi-tenancy |

Exact pricing should be validated experimentally against willingness to pay and AI unit economics.

# 13. Phase 4 — Web & Android

After Telegram retention and learning value are validated, expose the same application/domain APIs to richer clients.

Responsive web application.

Android application.

Unified authentication and student profile.

Image capture directly from mobile camera.

Better answer-page ordering and crop/quality guidance.

Rich progress dashboards.

Study-plan calendar.

Push notifications.

Same backend, AI Gateway, RAG, evaluation, and learning services.

# 14. Phase 4 — Scale Architecture

Scale only the components that demonstrate actual load.

| Component | Initial | Scale Trigger |
| --- | --- | --- |
| API | Single/few stateless instances | CPU/latency/traffic growth |
| Workers | Small BullMQ pool | Queue age/backlog |
| PostgreSQL | Managed PostgreSQL | Connection/query/storage pressure |
| Redis | Managed Redis | Queue/cache pressure |
| Object storage | S3-compatible | Image volume |
| AI Gateway | Provider abstraction | Volume/provider resilience |
| RAG | pgvector | Retrieval latency/corpus size |
| Analytics | Postgres initially | Event volume/reporting load |

# 15. Migration Strategy From Current Node.js Application

The migration must be incremental and reversible.

Freeze a known-good baseline and tag it.

Add tests around current behavior before moving logic.

Introduce TypeScript where appropriate without forcing a full rewrite.

Create domain/application modules around existing Telegram handlers.

Move AI calls behind AI Gateway adapters.

Move heavy operations into BullMQ workers.

Introduce PostgreSQL repositories and explicit transactions.

Add object storage abstraction for images.

Introduce RAG as an isolated module.

Introduce Evaluation Blueprint storage.

Route existing flows through the new modules.

Remove duplicated legacy code only after equivalent tests pass.

# 16. Recommended Repository Shape

apps/
  api/
  worker/
  scheduler/
  admin/
  web/                 # later

packages/
  domain/
  application/
  db/
  ai-gateway/
  rag/
  ocr/
  evaluation/
  questions/
  learning/
  telegram/
  storage/
  notifications/
  analytics/
  security/
  shared/

tests/
  unit/
  integration/
  e2e/
  ai/
  rag/
  ocr/
  security/
  load/

benchmarks/
  ai-gold-set/
  rag-gold-set/
  ocr-gold-set/

# 17. Engineering Workstreams

| Workstream | Primary Responsibility |
| --- | --- |
| Product/domain | Business rules and student journeys |
| Backend | APIs, persistence, jobs, integrations |
| AI | Prompts, model routing, structured outputs |
| RAG | Corpus, ingestion, retrieval, provenance |
| Vision/OCR | Handwriting extraction and confidence |
| Evaluation | Rubrics, blueprint, scoring, feedback |
| Learning | Skill profile and adaptive selection |
| Frontend | Web/Android when introduced |
| Telegram | Conversation UX and adapter |
| DevOps | CI/CD, infrastructure, monitoring |
| QA | Automated and AI benchmark testing |
| Content | PYQ/NCERT/source curation |
| Business | Pricing, growth, partnerships |

# 18. AI Model Strategy

Keep all model calls behind AI Gateway.

Use task-specific model routing rather than one model for everything.

Use stronger models for difficult evaluation or quality-critical cases.

Use lower-cost models for classification, tagging, simple transformations, and some retrieval tasks when benchmarked.

Cache stable outputs where safe.

Use asynchronous processing for non-interactive expensive operations.

Track provider/model performance continuously.

Maintain fallback providers/models for critical operations where practical.

# 19. Cost-Control Roadmap

| Optimization | When |
| --- | --- |
| Token/cost logging | Phase 0 |
| Avoid full-corpus prompts | Phase 1 |
| Evaluation Blueprint reuse | Phase 1 |
| Targeted RAG context | Phase 1 |
| Caching | Phase 1–2 |
| Model routing | Phase 2 |
| Batch/offline processing | Phase 2–3 |
| Cost-aware feature gating | Phase 3 |
| Provider optimization | Phase 3–4 |

Primary unit-economics metric: AI cost per successful learning attempt, not simply cost per API call.

# 20. Knowledge Base Rollout

Verify and structure BPSC PYQs.

Register source metadata and provenance.

Ingest approved NCERT material.

Chunk and embed content.

Create retrieval filters and source tiers.

Build RAG Gold Set.

Add authoritative government sources.

Add controlled current-affairs sources.

Introduce Bihar-specific verified material.

Continuously review source freshness and conflicts.

# 21. Content Governance

Every source has owner, type, authority tier, version, and ingestion status.

PYQs must be verified before entering the trusted corpus.

Current-affairs sources must carry publication/effective dates.

Conflicting information must be flagged rather than silently merged.

Deleted or superseded sources remain traceable in historical AI traces.

Content reviewers can disable problematic chunks without code deployment.

# 22. AI Quality Roadmap

| Stage | AI Quality Objective |
| --- | --- |
| MVP | Valid structured output and basic factual grounding |
| Production | Stable question quality and examiner rubric behavior |
| Beta | Human-vs-AI scoring benchmark |
| Personalization | Reliable weakness/skill signals |
| Scale | Continuous model/prompt regression |
| Advanced | Multi-model verification and calibrated confidence |

# 23. QA & Release Roadmap

Every release runs deterministic tests.

AI changes run relevant Gold Set benchmarks.

RAG changes run retrieval/grounding benchmarks.

OCR changes run handwriting benchmarks.

Security checks run in CI.

Staging runs smoke tests.

Critical regression triggers rollback.

Production quality metrics are monitored after deployment.

# 24. Analytics Roadmap

| Stage | Analytics |
| --- | --- |
| Phase 0 | AI call, error, latency, cost logging |
| Phase 1 | Student journey and attempt funnel |
| Phase 2 | Skill and learning analytics |
| Phase 3 | Cohorts, retention, conversion, experiments |
| Phase 4 | Cross-client analytics and advanced personalization |

North-Star Metric: Weekly Active Learning Students (WALS), supplemented by meaningful completed attempts and measurable improvement.

# 25. Security & Privacy Roadmap

Secure authentication and authorization.

Student-owned resource checks.

Private object storage.

Signed URLs with short expiry.

Upload validation.

Secret management.

Prompt-injection defense.

Audit logs for sensitive administrative actions.

Retention/deletion controls.

Provider data-processing review.

Incident response.

Periodic security testing.

# 26. Production Readiness Checklist

| Area | Ready When |
| --- | --- |
| Core journey | Question-to-evaluation flow works reliably |
| Data | Backups and restore process tested |
| AI | Provider failures and malformed outputs handled |
| RAG | Evidence/provenance works |
| OCR | Representative handwriting benchmark passes |
| QA | Critical regression suite passes |
| Security | No unresolved critical findings |
| Observability | Alerts and traces available |
| Cost | Unit economics understood |
| Operations | Runbooks and ownership defined |
| Support | Student issue path defined |
| Rollback | Known-good version/config can be restored |

# 27. Launch Criteria

Core journey success rate meets agreed threshold.

AI examiner benchmark meets expert-approved threshold.

Question quality gate prevents unsafe/poor questions.

RAG grounding benchmark passes.

OCR benchmark is acceptable for supported handwriting conditions.

Critical security tests pass.

AI cost per attempt is economically viable.

Monitoring and alerts are active.

Data retention and deletion processes are documented.

Support and incident ownership are established.

# 28. First 90-Day Execution Plan

| Period | Priority |
| --- | --- |
| Days 1–15 | Repository audit, architecture mapping, tests, AI call inventory, security baseline |
| Days 16–30 | AI Gateway, DB/domain cleanup, queues, storage abstraction, observability |
| Days 31–45 | Question pipeline, Quality Checker, Evaluation Blueprint, RAG foundation |
| Days 46–60 | OCR pipeline, examiner pipeline, Telegram end-to-end flow |
| Days 61–75 | Gold Sets, human benchmark, regression suite, admin quality tools |
| Days 76–90 | Beta hardening, analytics, cost optimization, security/load testing |

# 29. Claude Code Master Execution Prompt

Claude Code should treat Documents 01–12 as the product specification set. Before modifying code, inspect the existing repository and produce a gap analysis against these documents. Do not perform a blind rewrite.

Preserve working behavior unless the specification explicitly changes it.

Implement one vertical slice at a time.

Before each major refactor, add tests around existing behavior.

Create explicit interfaces at external boundaries.

Never hard-code a model provider inside business logic.

Never pass the full knowledge corpus to an LLM when retrieval can supply relevant evidence.

Persist question lineage and Evaluation Blueprint.

Preserve original handwriting images and OCR versions.

Make AI jobs asynchronous where latency permits.

Add observability before scaling.

Do not mark a task complete without tests.

After each milestone, run the relevant regression suite and report files changed, tests run, failures, and remaining risks.

# 30. Claude Code Milestone Order

Repository and architecture audit.

Baseline test suite.

Domain/module boundaries.

Database/migration hardening.

AI Gateway.

Queue/worker infrastructure.

Question generation + quality gate.

Evaluation Blueprint.

RAG ingestion/retrieval.

OCR/Vision pipeline.

Examiner evaluation.

Telegram end-to-end integration.

Learning profile.

Adaptive question selection.

Analytics.

Admin quality review.

Security hardening.

Load/reliability testing.

Beta readiness.

Web/Android preparation.

# 31. Product Moat

The defensible advantage is not the underlying LLM. It is the combination of curated BPSC knowledge, verified PYQ lineage, evaluation blueprints, expert-calibrated rubrics, handwritten-answer data, longitudinal learning signals, and adaptive practice.

Question lineage becomes proprietary structured knowledge.

Evaluation traces become a benchmark for answer-writing quality.

Student histories enable personalization.

Human-vs-AI benchmark data improves reliability.

Content governance improves trust.

Repeated attempts create a learning dataset that generic AI assistants do not naturally possess.

# 32. Long-Term Product Expansion

BPSC Prelims practice.

BPSC Mains answer writing.

Essay evaluation.

Interview preparation.

Daily current-affairs practice.

Bihar-specific knowledge modules.

Teacher/institute dashboards.

Cohort assignments.

Peer or mentor review.

Multi-exam expansion after BPSC product-market fit.

Expansion should follow the same platform primitives rather than creating separate AI systems for every exam.

# 33. Key Risks & Mitigation

| Risk | Mitigation |
| --- | --- |
| AI score inconsistency | Blueprint + rubric + human benchmark |
| OCR errors | Confidence + original images + reprocessing |
| Hallucination | RAG + provenance + authority hierarchy |
| AI cost explosion | Gateway + routing + caching + budgets |
| Overengineering | Modular monolith first |
| Poor retention | Adaptive learning and measurable improvement |
| Content errors | Source governance and review |
| Vendor lock-in | Provider abstraction |
| Security incident | Least privilege + validation + monitoring |
| Scaling too early | Metrics-driven extraction |

# 34. Final Architecture-to-Execution Trace

PRODUCT REQUIREMENTS → DOMAIN MODEL → APIs → JOBS → AI GATEWAY → RAG → OCR → EVALUATION BLUEPRINT → EXAMINER → FEEDBACK → LEARNING PROFILE → ANALYTICS → QA BENCHMARKS → PRODUCTION OBSERVABILITY → ITERATION

This trace should remain visible throughout implementation so individual technical decisions can always be connected to the student outcome.

# 35. Final Definition of Done

The existing application has been mapped and safely refactored rather than blindly rewritten.

The complete student learning loop works end-to-end.

All AI providers are abstracted behind AI Gateway.

Questions have lineage and Evaluation Blueprints.

RAG supplies traceable evidence.

Handwritten images are preserved and OCR is repeatable.

Examiner scoring is benchmarked against human reviewers.

Student weaknesses and progress are persisted.

Next-question selection can use learning signals.

Critical flows are covered by automated tests.

AI/RAG/OCR regression suites are operational.

Security, privacy, backup, monitoring, and rollback are production-ready.

AI cost per learning attempt is measurable.

Telegram remains a stable client while future Web/Android clients reuse the same backend.

Product decisions are driven by learning outcomes and retention, not vanity usage.

# 36. Final Product Principle

Build the smallest system that can reliably produce a complete learning loop, measure whether it improves students, and then make that loop smarter. Do not start by building a giant AI platform. Start by building a trustworthy BPSC mentor.

The strategic sequence is: TRUST → RELIABILITY → LEARNING VALUE → PERSONALIZATION → RETENTION → MONETIZATION → SCALE.

Documents 01–12 together form the implementation baseline. Claude Code should use them as the source of truth, while treating explicit product-owner decisions and verified production constraints as higher-priority inputs when they evolve.